## KPI Cards
BET | Primary KPI | Secondary KPIs
Ads

## KPIs
Metric | Current | Last Period
Tot Revenue Delivered (M) | 464404 | 382404
Ads Revenues (M) | 151822 | 73822
Brand Revenues (M) | 312582 | 308582
BI Advertiser Value | 358 | 341
Account Linkage | 1.0K | 1.0K

## Initiatives
| Links | Start | Launch | Stage | Status | Update
KEY INITIATIVES
Prebid Experimentation (display & outstream) | PRD | 2025-11-01 | 2025-12-18 | 🚀 Launched | 💚 On Track | Goal if we can replace our monetisation partners with an in-house prebid solution inherited from Mobalytics
Skin Initiative | PRD | 2025-12-01 | 2026-04-01 | 🚢 Deploy | 💚 On Track | Create a new skin features that we can monetise in with a trading partner
Peripherals Initiative (Discovery) | PRD | 2026-01-14 | 2026-04-01 | 🚢 Deploy | 💚 On Track | Create a new features for hardware components that we can monetise in with a trading partner
Play Interstitial | PRD | 2026-02-19 | 2026-04-01 | 🎨 Design | ⚠️ At Risk | A new premium ad format to increase eCPMs on the current interstitial
OPTIMISATION
Viewability Optimisation Experiments | PRD | 2025-10-01 | 2025-11-09 | 🚧 Develop | 🚨 Off Track | a series of experiments to improve the performances of our current and new ad formats
Retool Internal data | PRD | 2025-10-01 | 2025-12-15 | 🚀 Launched | 💚 On Track | Replace Looker with a Retool to remove any data eng / science dependencies
Advertiser Portal v2 | PRD | 2025-10-02 | 2026-12-16 | 🚧 Develop | 💚 On Track | Improve the advertiser dashboard for our Brand Integration partners
Mystery Box Experiment | PRD | 2025-12-01 | 2026-04-01 | 🔍 Analyzed & Complete | 💚 On Track | Experiment if the psychological frame of the secret reward might increase Mission completion rate
Logitech Branded Event | PRD | 2025-12-01 | 2026-02-18 | 🔍 Analyzed & Complete | 💚 On Track | Custom Branded Event to drive the Logitech KPI on their new mouse launch "PRO X2 SUPERSTRIKE"

## Team
Product & Design | 1 | PM | 1 | PD
Tech | 1 | EM | 1 | BE | 1 | FE
Total | 5

## Initiatives BACKUP
| Links | Start | Launch | Stage | Status | Update
KR1: Convert 30K users to make a first time deposit
Mission 3.0: Mapping & Experimenting the User behaviour | PRD | 2024-07-01 | 2024-09-01 | 🚀 Launched | 💚 On Track | Refinement ready to go after Subs review
Custom Drops | PRD | 2024-07-01 | 2024-09-01 | 🎨 Design | 💚 On Track
KR2: Add 150K new users with unlinked accounts
Account linkage 2.0: mission game agnostic & drops to drive AL | PRD | 2024-07-01 | 2024-09-01 | 🚀 Launched | 💚 On Track
AL on Mobile | PRD | 2024-07-01 | 2024-09-01 | New | 🛑 On Hold
KR3: Activate all 54 Missions and Branded combined competitions scheduled, on time
Upload assets & auto-adjust | PRD | 2024-07-01 | 2024-09-01 | 🚧 Develop | 💚 On Track
Admin panel for CDP segmentation | PRD | 2024-07-01 | 2024-09-01 | 🚧 Develop | 💚 On Track
Organizer Self serve Campaign report | PRD | 2024-07-01 | 2024-09-01 | New | 🛑 On Hold
KR4: Validate MVP Broadcast drop as a new branded product
POC Twitch extension with Faceit points for validation | PRD | 2024-07-01 | 2024-09-01 | 🔍 Analyzed & Complete | 💚 On Track
Reusing the current Drops service | PRD | 2024-07-01 | 2024-09-01 | 🚧 Develop | 💚 On Track
Outside OKRs
D-Telekom Portal |  | 2024-07-01 | 2024-09-01 | 🔍 Analyzed & Complete | 💚 On Track
OM SKD on Watch Ads |  | 2024-07-01 | 2024-09-01 | 🔍 Analyzed & Complete | 💚 On Track
Mid-Rolls Watch IEM Cologne |  | 2024-07-01 | 2024-09-01 | 🔍 Analyzed & Complete | 💚 On Track
Qiddiya custom maps |  | 2024-07-01 | 2024-09-01 | 🚧 Develop | 💚 On Track
HLTV Winline |  | 2024-07-01 | 2024-09-01 | 🚢 Deploy | 💚 On Track
Watch Drops Admin |  | 2024-07-01 | 2024-09-01 | 🚧 Develop | ⚠️ At Risk